## Sheet1
S.N. | Task | Assigned To | Estimated Hours | Date | 19-02-2014
1 | Template Display and load | Gajendra | 5 | 21-02-2014
2 | Update Code according to Database Structure | Gajendra | 12 | 20-02-2014
3 | Create Demo Categories with image upload functionality in backend | Gajendra | 7 | 20-02-2014 | Add Task Type assignment checkbox in category, Adjust parent-child category
4 | Create Demo Questions for Categories | Gajendra | 3 | 20-02-2014 | Create master for category questions
5 | Private invitation list | Gajendra | 7 | 25-02-2014
6 | Task Preview | Gajendra | 12 | 20-02-2014
7 | Task Detail Page | Gajendra | 10 | 22-02-2014
8 | Skill Management in backend | Gajendra | 9 | 21-02-2014
9 | Logging | Gajendra | 9 | 28-02-2014
10 | Tasks Listing in backend | Gajendra | 8 | 26-02-2014
11 | Task Proposal | Gajendra | 7 | 24-02-2014
12 | Implement category questions on create task page | Mukul | 6 | 22-02-2014
13 | Implement Skill selection on create task page | Mukul | 6 | 22-02-2014
14 | Task Type and Category loading with create task form | Mukul | 12 | 19-02-2014
15 | Description Text counter | Mukul | 1 | 19-02-2014
16 | Task Invitation | Mukul | 12 | 21-02-2014
17 | HTML Creation and partials creation on Create Task Page | Mukul | 10 | 19-02-2014
18 | Task List | Mukul | 10 | 24-02-2014
19 | Edit Form | Mukul | 18 | 20-02-2014
20 | Add / Edit Attachements | Mukul | 10 | 20-02-2014
21 | Notifications | Mukul | 5 | 26-02-2014
22 | Template Creation | Virendra | 12 | 20-02-2014
23 | Database Updation | Virendra | 10 | whenever required
24 | Code Reviews | Virendra | 25 | daily
25 | Conversation with Ajay sir and implement changes suggested by him | Virendra | 10 | whenever scheduled
26 | Understanding of projects | Virendra | 5 | 21-02-2014
27 | Resolve issues | Virendra | 12 | daily

## Sheet2
S.N. | Task | Assigned To | Estimated Hours | Date | Status
1 | Update Code according to Database Structure | Gajendra | 12 | 20-02-2014
2 | Create Demo Categories with image upload functionality in backend | Gajendra | 7 | 20-02-2014
3 | Create Demo Questions for Categories | Gajendra | 3 | 20-02-2014
4 | Task Preview | Gajendra | 8 | 20-02-2014
5 | Save lat long while saving profile address | Gajendra | 2 | 21-02-2014
6 | Template Display and load | Gajendra | 5 | 21-02-2014
7 | Skill Management in backend | Gajendra | 9 | 21-02-2014
8 | Task Detail Page | Gajendra | 10 | 22-02-2014
9 | Task Proposal | Gajendra | 8 | 24-02-2014
10 | Private invitation list | Gajendra | 7 | 25-02-2014
11 | Tasks Listing in backend | Gajendra | 8 | 26-02-2014
12 | Logging | Gajendra | 9 | 27-02-2014
13 | Task Type and Category loading with create task form | Mukul | 12 | 19-02-2014 | Done
14 | Description Text counter | Mukul | 1 | 19-02-2014
15 | HTML Creation and partials creation on Create Task Page | Mukul | 10 | 19-02-2014
16 | Edit Form | Mukul | 18 | 20-02-2014
17 | Add / Edit Attachements | Mukul | 10 | 20-02-2014
18 | Task Invitation | Mukul | 12 | 21-02-2014
19 | Implement category questions on create task page | Mukul | 6 | 22-02-2014
20 | Implement Skill selection on create task page | Mukul | 6 | 22-02-2014
21 | Task List | Mukul | 10 | 24-02-2014
22 | Notifications | Mukul | 5 | 25-02-2014
23 | Template Creation | Virendra | 12 | 20-02-2014
24 | Database Updation | Virendra | 10 | whenever required
25 | Code Reviews | Virendra | 25 | daily
26 | Conversation with Ajay sir and implement changes suggested by him | Virendra | 10 | whenever scheduled
27 | Understanding of projects | Virendra | 5 | 21-02-2014
28 | Resolve issues | Virendra | 12 | daily