## April
S.N. | Task | Assigned To | Estimated Hours | Date
| Demo Data using functional flow | Archana | 18 | 02-04-2014
| SocialMedia Signup/login | Archana | 35 | 07-04-2014
| Email Templates | Archana | 15 | 09-04-2014
| New Registration Verification Mail | Archana | 6 | 10-04-2014
| ForgotPassword Mail | Archana | 5 | 10-04-2014
| Social Media Share | Archana | 22 | 15-04-2014
| Reviews | Gajendra | 13 | 16-04-2014
| Comments | Gajendra | 25 | 19-04-2014
| Ratings | Gajendra | 21 | 23-04-2014
| Notifications | Gajendra | 16 | 25-04-2014
| Task Completion | Gajendra | 18 | 29-04-2014
| Bug fixes in testing | Gajendra | 9 | 30-04-2014
| Fix issues on live server | Mukul | 18 | 02-04-2014
| Map View Implementation | Mukul | 9 | 03-04-2014
| Validations before create task | Mukul | 17 | 05-04-2014
| Proposal List | Mukul | 27 | 09-04-2014
| Proposal Detail | Mukul | 19 | 11-04-2014
| Inbox | Mukul | 42 | 18-04-2014
| Search/filter Tasker in task list | Mukul | 62 | 29-04-2014
| Save Search / Filter + issue fixing | Mukul | 9 | 30-04-2014
| Designing fixes/changes based on wireframe and discussion | Virendra | 25
| Code review | Virendra | 35
| Flow + functionality testing | Virendra | 25
| Escrow process | Virendra | 20
| Requirement analysis | Virendra | 25
| Prepare base for API | Virendra | 8
| R&D on chat | Virendra | 18
| R&D on voice chat | Virendra | 32
| Asynchronous Mail/Message implementation / testing | Virendra | 18
| API (getToken, Login, Logout, Register, changePassword, ForgotPassword, createProfile, UpdateProfile, CreateTask, UpdateTask,MyTaskList, TaskList) | Archana | 50 | 21-04-2014

## All Pending Tasks
S.N. | Task | Month
1 | Advance /smart Search | May
2 | Profile Settings | May
3 | Team Creation | May
4 | Invite taskers to join team | May
5 | Leave team | May
6 | Escrow Process
7 | Milestone Creation
8 | Milestone Completion
9 | Milestone Release Payment
10 | Advance Inbox | May
11 | Text chat live | May
12 | Voice chat
13 | Video chat
14 | Push Notification on mobile | May
15 | Domain templates
16 | Background verification
17 | Safety check process
18 | Payment Integration
19 | Invoice generation
20 | Task completion | May
21 | Transaction History
22 | References / recommendations
23 | Network member management
24 | Calendar Meeting schedular
25 | Fraud detection / prevention
26 | Removal of unwanted / old entries from db
27 | Task Management in Admin
28 | User Management in Admin
29 | Latest activity in frontend | May
30 | User report in admin
31 | Payment report in admin
32 | Favourite in frontend | May
33 | Task Report in admin
34 | Chart report in admin
35 | Charts in user dashboard
36 | Reminder mails / messages for various activities | May
37 | Task Cancel handling
38 | Task hold handling
39 | Help Page
40 | T & C page
41 | Upload receipts
42 | Sign in as Available for Instant | May
43 | User Dashboard
44 | Release Payment from escrow
45 | Dispute Resolution
46 | Social media signup / login | April
47 | Social media share | April
48 | Email Templates | April
49 | New Registration Verification Mail | April
50 | ForgotPassword Mail | April
51 | Reviews | April
52 | Comments | April
53 | Ratings | April
54 | Notifications | April
55 | Task Completion | April
56 | Bug fixes in testing | April
57 | Fixe issues on live server | April
58 | Map View Implementation | April
59 | Validations before create task | April
60 | Proposal List | April
61 | Proposal Detail | April
62 | Inbox | April
63 | Search/filter Tasker in task list | April
64 | Save Search / Filter + issue fixing | April
65 | Search/filter task in task list | April
66 | My tasks as poster | April
67 | My tasks as tasker | April
68 | Inbox messsage detail page | April
69 | Company Signup
70 | Company Payment
71 | Company Professional membership

## May
S.N. | Task | Assigned To | Estimated Hours | Date
| Demo Data using functional flow | Archana | 12 | 02-04-2014
| SocialMedia Share task | Archana | 35 | 07-04-2014
| Email Templates | Archana | 15 | 09-04-2014
| Inbox page | Mukul | 12 | 10-05-2014
| Inbox detail page | Mukul | 12 | 10-05-2014
| Rating by tasker | Mukul | 22 | 15-05-2014
| Review by tasker | Mukul | 13 | 16-05-2014
| Rating by poster | Mukul | 25 | 19-05-2014
| Review by poster | Mukul | 21 | 23-05-2014
| Notifications list | Gajendra | 24 | 25-04-2014
| Task Completion By Tasker | Mukul | 15 | 03-05-2014
| Task Completion By Poster | Mukul | 15 | 06-05-2014
| Notifications settings | Gajendra | 16 | 30-04-2014
| Map View Implementation | Mukul | 3 | 06-05-2014
| Favorite taskers list | Gajendra | 5 | 05-04-2014
| Favorite posters list | Gajendra | 5 | 09-04-2014
| Inbox tag system | Mukul | 19 | 11-05-2014
| Notifications emails | Gajendra | 20 | 18-04-2014
| Save Search / Filter + issue fixing | Mukul | 9 | 01-05-2014
| Designing fixes/changes based on wireframe and discussion | Virendra | 25
| Code review | Virendra | 25
| Flow + functionality testing | Virendra | 25
| Payment process | Virendra | 20
| Requirement analysis | Virendra | 25
| Prepare base for API | Virendra | 8
| R&D on chat | Virendra | 18
| R&D on voice chat | Virendra | 32
| Asynchronous Mail/Message implementation / testing | Virendra | 18
Travel Project Database
Travel Project setup
| API (getToken, Login, Logout, Register, changePassword, ForgotPassword, createProfile, UpdateProfile, CreateTask, UpdateTask,MyTaskList, TaskList) | Archana | 50 | 21-04-2014

## Sheet1
Payment process
Prepare base for API
Instant chat
voice chat
Video chat
Asynchronous Mail/Message implementation / testing
Background check / sterling
Server Maintenance
Mirror Server
Server Backup and Restore
Support ticket system
Load balancing
Push Notifications
Upgrade to Yii 2.0 version

## Sheet2
S.N. | Task | Assigned To | Estimated Hours | Date
| Virtual Task Create / Edit | Mukul | 25 | 19-05-2014
| InPerson Task Create / Edit | Mukul | 15 | 22-05-2014
| Instant Task Create / Edit | Mukul | 20 | 27-05-2014
| Notification Settings for user | Gajendra | 10 | 17-05-2014
| Notification display page | Gajendra | 5 | 17-05-2014
| Project Completion by doer | Gajendra | 14 | 20-05-2014
| Message Central | Gajendra | 24 | 23-05-2014
| Message Central Detail | Gajendra | 24 | 28-05-2014
| Payment API | Virendra | 36 | 30-05-2014
| Prepare base for API | Virendra | 8 | 31-05-2014
| R&D on chat | Virendra | 18 | 17-05-2014
| R&D on voice chat | Virendra | 32 | 23-05-2014
| Asynchronous Mail/Message implementation / testing | Virendra | 18 | 20-05-2014
| Map View Implementation | Mukul | 5 | 06-05-2014
| Inbox tag system | Mukul | 19 | 11-05-2014
| Save Search / Filter + issue fixing | Mukul | 9 | 01-05-2014
| Designing fixes/changes based on wireframe and discussion | Virendra | 25
| Code review | Virendra | 25
| Flow + functionality testing | Virendra | 25
| Payment process | Virendra | 20
| Requirement analysis | Virendra | 25
| Prepare base for API | Virendra | 8
| R&D on chat | Virendra | 18
| R&D on voice chat | Virendra | 32
| Asynchronous Mail/Message implementation / testing | Virendra | 18
Travel Project Database
Travel Project setup
| API (getToken, Login, Logout, Register, changePassword, ForgotPassword, createProfile, UpdateProfile, CreateTask, UpdateTask,MyTaskList, TaskList) | Archana | 50 | 21-04-2014

## Sheet3
Week | Module | Tasks planned for delivery | Pending
26-31 may | Create Task | Create Virtual Task | Background Check Verification
|  | Create InPerson Task | Notifications Email
|  | Edit Virtual Task | Push Notification
|  | Edit InPerson Task | Sms Notification
Escrow from poster account to site admin account
| Notification | Manage Notification Settings by user
Create Database tables to manage Email Notifications
Email notification on create task
| Notification | Notifications page display on website
Default setting for min price, max price, estimated hours in admin