## Front End
Priority | Name for Page/Screen | Module Status | URL's | Pre Initial Wireframe by A I / Client Team | [5 empty] | After Development completed | [8 empty] | Pending Issues
|  |  |  | Initial Design |  | UI Comments by Matthew |  | Functionality by Brad |  | Development Work Submitted |  | UI Approval |  | Functional Approval |  | Code Approval |  | Complete Status
|  |  |  | Date | Remarks | Date | Remarks | Date | Remarks | Date | Remarks | Status | Remarks | Status | Remarks | Status | Remarks
| Landing Page | [16 empty] | Not Approved
| Sign In | Working | http://122.176.45.15:8080/greencomet/ | [14 empty] | Not Approved | Login through social media sites
| Recover Lost Password | [16 empty] | Not Approved
| Marketing Page for Taskers | Planned in next month delivery | [15 empty] | Not Approved
| Marketing Page for Posters | Planned in next month delivery | [15 empty] | Not Approved
| Create Membership Account | Working | http://122.176.45.15:8080/greencomet/ | [14 empty] | Not Approved | Signup with social media site
| Create Escrow Account | [16 empty] | Not Approved
| Create User Profile | Done | http://122.176.45.15:8080/greencomet/index/updateprofile | [14 empty] | Not Approved | record lat long when user updates profile
| Sign-up for Safety Check | [16 empty] | Not Approved
| Pass Safety Check | [16 empty] | Not Approved
| Fail Safety Check | [16 empty] | Not Approved
| Marketing Page for Premium Membership | [16 empty] | Not Approved
| Subscribe to Premium Level | [16 empty] | Not Approved
| Pass Premium Background Check | [16 empty] | Not Approved
| Fail Premium Background Check | [16 empty] | Not Approved
| Create Virtual Task | Done | http://122.176.45.15:8080/greencomet/poster/createtask | [14 empty] | Not Approved
| Create Instant Task | Done | http://122.176.45.15:8080/greencomet/poster/createtask | [14 empty] | Not Approved
| Sign in as "Available" for Instant Task | [16 empty] | Not Approved
| Create In-Person Task | Done | http://122.176.45.15:8080/greencomet/poster/createtask | [14 empty] | Not Approved
| View Portfolio/Gallery | Working | [15 empty] | Not Approved
| Search for Posted Tasks | [16 empty] | Not Approved
| Posted Task Detail | Working | [15 empty] | Not Approved
| Search for Taskers | [16 empty] | Not Approved
| Tasker Public Profile | Working | [15 empty] | Not Approved
| Complete the Task | [16 empty] | Not Approved
| Upload Receipts | [16 empty] | Not Approved
| Release Payment from escrow | [16 empty] | Not Approved
| Rate and Review Tasker | Planned in next month delivery | [15 empty] | Not Approved
| Rate and Review Poster | Planned in next month delivery | [15 empty] | Not Approved
| Moderation Queue | [16 empty] | Not Approved
| User Dashboad | Planned in next month delivery | [15 empty] | Not Approved
| Create New Team | [16 empty] | Not Approved
| Invite Taskers to Join Team | [16 empty] | Not Approved
| Join Team | [16 empty] | Not Approved
| Leave Team | [16 empty] | Not Approved
| Manage Portfolio/Gallery Files | Planned in next month delivery | [15 empty] | Not Approved
| Manage Escrow Account | [16 empty] | Not Approved
| Notifications | Planned in next month delivery | [15 empty] | Not Approved
| Recommendations | [16 empty] | Not Approved
| Manage Premium Membership | [16 empty] | Not Approved
| Manage Escrow Account | [16 empty] | Not Approved
| Manage Past Invoices Screen | [16 empty] | Not Approved
| Manage Past Earnings Statements Screen | [16 empty] | Not Approved
| Manage Email Subscriptions | [16 empty] | Not Approved
| Manage Connections | [16 empty] | Not Approved
| Messages | [16 empty] | Not Approved
| Compose New Message | Planned in next month delivery | [15 empty] | Not Approved
| FAQ | [16 empty] | Not Approved
| Terms and Conditions | [16 empty] | Not Approved
| Need Help | [16 empty] | Not Approved
| How to Use | [16 empty] | Not Approved

## Back End
Priority | Name for Page/Screen | Module Status | URL's | Pre Initial Wireframe by A I / Client Team | [5 empty] | After Development completed | [8 empty] | Pending Issues
|  |  |  | Initial Design |  | UI Comments by Matthew |  | Functionality by Brad |  | Development Work Submitted |  | UI Approval |  | Functional Approval |  | Code Approval |  | Complete Status
|  |  |  | Date | Remarks | Date | Remarks | Date | Remarks | Date | Remarks | Status | Remarks | Status | Remarks | Status | Remarks
| Sign In | Done | http://122.176.45.15:8080/greencomet/admin | [14 empty] | Not Approved
| Language Management | Done | http://122.176.45.15:8080/greencomet/admin/language/admin | [14 empty] | Not Approved
| Country Management | Done | http://122.176.45.15:8080/greencomet/admin/country/admin | [14 empty] | Not Approved
| State Management | Done | http://122.176.45.15:8080/greencomet/admin/state/admin | [14 empty] | Not Approved
| Region Management | Done | http://122.176.45.15:8080/greencomet/admin/region/admin | [14 empty] | Not Approved
| City Management | Done | http://122.176.45.15:8080/greencomet/admin/city/admin | [14 empty] | Not Approved
| Category Management | Done | http://122.176.45.15:8080/greencomet/admin/category/admin | [14 empty] | Not Approved
| Category Questions Management | Done | http://122.176.45.15:8080/greencomet/admin/categoryquestion/admin | [14 empty] | Not Approved
| Category Templates create/update | Done | http://122.176.45.15:8080/greencomet/admin/category/create | [14 empty] | Not Approved
| Category Skill Management | Done | http://122.176.45.15:8080/greencomet/admin/skill/admin | [14 empty] | Not Approved
| Task List | Done | http://122.176.45.15:8080/greencomet/admin/task/admin | [14 empty] | Not Approved
| Admin Users Management | Done | http://122.176.45.15:8080/greencomet/admin/admin/admin | [14 empty] | Not Approved
| Admin Roles Management | Done | http://122.176.45.15:8080/greencomet/admin/roles/admin | [14 empty] | Not Approved