## Sheet1
Date | Task | Est. Time (Hrs) | Sub-Task
2013-12-02 | YII Framework installation | 8 | Stablish Basic structure
Basic requirements
Ceate working test app
Connect with mysql database
Study folder structure
2013-12-03 | Study YII Framework Configuration | 4 | Configure APACHE, MYSQL again because servces were not working
Update PHP version 5.2 to 5.5 because we need upgrded version for better support else lots of functions will not support
2013-12-04 | Study YII Framework Configuration | 8 | Declare Folder structure
Separate controller for front and back (Admin)
Separate views for front and back (Admin)
Common Database setting for front and back (Admin)
Global setting variable declaration
Separate default URL settting for front and back (Admin)
Separate URL handler for front and back (Admin)
2013-12-05 | Study YII Framework Configuration | 8 | Multi Language Support (Messages + Labels)
2013-12-06 | Study YII Framework Configuration | 8 | Textbox placeholder
Form Fields -- Datepicker, Dropdown, Checkbox, Radio
How widget works?
Working with datagrids -- continued
2013-12-07 | Study YII Framework Configuration | 5 | Working with datagrids -- DONE
How to implement paging
2013-12-09 | Study YII Framework Configuration | 7 | Dynamic Date conversion according to selected language.
Working with SUBQUERY
Dropdown added to change no of records in dtagrid
2013-12-10 | Study YII Framework Configuration |  | How to use extensions
Graph (Chart) Implamneted on test page
Created final base project
2013-12-11 | Study YII Framework Configuration |  | Access rules implemented for different types of user.
2013-12-12 | Green Comet |  | Country module Started